## Sheet1
Product Backlog Item | Task (see Userstory.txt) | Volunteer | Status | Original Estimate (hrs) | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25
#1 As a computer programmer, I can manually input | Task 1 | Brett | Closed | 30
a file to create shapes. | Task 2 | David | Closed | 15
#2 As a computer programmer, I can receive verbose | Task 1 | Brett | Closed | 30
errors from the file parser | Task 2 | Brett | Closed | 10
#3 As a teacher, I can login to the program | Task 1 | Greg | Closed | 6
| Task 2 | David | Closed | 6
#4 As a user, I can create multiple logins | Task 1 | Justis | Closed | 3
| Task 2 | Greg | Closed | 3
| Task 3 | Greg | Closed | 3
#5 As a student, I can render shapes | Task 1 | Brett | Closed | 100
#6 As a student, I can define multiple shapes | Task 1 | Justis | Closed | 16
#7 As a user, I can change user-defined shapes | Task 1 | David | Closed | 5
and save to a file | Task 2 | David | Closed | 3
#8 As a student, I can calculate the dimensions, | Task 1 | Justis | Closed | 12
perimeter, or area of any shape | Task 2 | Justis | Closed | 12
#9 As a user, my username and password will be "encrypted" | Task 1 | Greg | In Progress | 18
#10 As a tester, I know who developed the program | Task 1 | Brett | Closed | 5
and who to contact if I discover bugs | Task 2 | Justis | Closed | 1