## Sheet1
Product Backlog Item | Task (see Userstory.txt) | Volunteer | Status | Original Estimate (hrs) | 2018-07-16 | 2018-07-17 | 2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23 | 2018-07-24 | 2018-07-25 | Sprint Reivew
#1 As a computer programmer, I can manually input a file to create shapes. | Task 1 | Brett | Closed | 30 | 2018-07-16: Completed in Sprint 1 | 0
| Task 2 | David | Closed | 15 | [10 empty] | 0
#2 As a computer programmer, I can receive verbose errors from the file parser | Task 1 | Brett | Closed | 30 | 2018-07-16: Completed in Sprint 1 | 0
| Task 2 | Brett | Closed | 10 | [10 empty] | 0
#3 As a teacher, I can login to the program | Task 1 | Greg | Closed | 6 | 2018-07-16: Completed in Sprint 1 | 0
| Task 2 | David | Closed | 6 | [10 empty] | 0
#4 As a user, I can create multiple logins | Task 1 | Justis | Closed | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 2 | Greg | Closed | 3 | 2018-07-16: Completed in Sprint 1 | 0
| Task 3 | Greg | Closed | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#5 As a student, I can render shapes | Task 1 | Brett | Closed | 100 | 1 | 1 | 6 | 6 | 6 | 0 | 6 | 0 | 0 | 0 | 0
#6 As a student, I can define multiple shapes | Task 1 | Justis | Closed | 16 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#7 As a user, I can change user-defined shapes and save to a file | Task 1 | David | Closed | 5 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task 2 | David | Closed | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 1 | 0
#8 As a student, I can calculate the dimensions, perimeter, or area of any shape | Task 1 | Justis | Closed | 12 | 2018-07-16: Completed in Sprint 1 | 0
| Task 2 | Justis | Closed | 12 | [10 empty] | 0
#9 As a user, my username and password will be "encrypted" | Task 1 | Greg | Discarded | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
#10 As a tester, I know who developed the program and who to contact if I discover bugs | Task 1 | Brett | Closed | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0
| Task 2 | Justis | Closed | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
|  |  |  | Total: | 9 | 3 | 13 | 10 | 8 | 0 | 9 | 8 | 2 | 1 | 0